# BDPH Enterprise Platform Development Timeline Proposal

Document version: 3.0 (Revised)
Revision date: 22 June 2026
Prepared for: BDPH / Client review
Platform: BDPH Enterprise Platform (Web + Mobile)

## Revision Summary

This document reflects cumulative client scope agreed through 22 June 2026. Revision 2.0 (17 June 2026) added six fleet safety and mobile operations modules. Revision 3.0 adds thirteen enhancements from the latest product discussion covering driver fuel capture, inventory analytics, live tracking intelligence, trip operations, and alerts.

| # | New Module | Category |
| --- | --- | --- |
| 1 | Share Vehicle Location | GPS / Communications |
| 2 | Nearby Vehicle (Issue / Accident) | GPS / Emergency Response |
| 3 | Breakdown Button (Driver Application) | Mobile / Safety |
| 4 | Fleet Mobile Application | Mobile |
| 5 | Helper (Crew Member) | Driver & Vehicle Management |
| 6 | Two Drivers in One Vehicle | Driver & Vehicle Management |

Note: Revisions 2.0 and 3.0 extend the original timeline. See Revised Project Duration below. MVP launch scope (web): Login, Dashboard, Tracking, Vehicles, Drivers, Trip & Operations, Fuel, Inventory, Documents.

Thirteen enhancements across fuel, inventory, tracking, trips, alerts, and mobile driver workflows.

## Revision 3.0 — Latest Client Discussion (22 June 2026)

| # | Feature | Module | Platform |
| --- | --- | --- | --- |
| 1 | Fuel Invoice OCR (Driver App) | Fuel | Mobile |
| 2 | Part Outward & Parts Consumption Analysis | Inventory | Web |
| 3 | Bulk Fuel Entry (Excel Import) | Fuel | Web |
| 4 | Alerts Page | Platform | Web + Mobile |
| 5 | Vehicle Status Count (Live Tracking) | Tracking | Web |
| 6 | Date & Time on Trip Page | Trip & Operations | Web |
| 7 | Location-Based Idle & Harsh Acceleration | Tracking / Telematics | Web + Mobile |
| 8 | Vehicle Icon Upload | Vehicles | Web |
| 9 | Vehicle Heading Arrow | Tracking | Web + Mobile |
| 10 | Multi-Vehicle Search (Live Tracking) | Tracking | Web |
| 11 | Nearby Vehicle Identification (All Vehicles) | Tracking | Web + Mobile |
| 12 | Vendor & Route Filter (Live Tracking) | Tracking | Web |
| 13 | Driver Reroute on Route Change | Trip & Operations | Mobile + Web |

## Project Overview

This proposal outlines the estimated development timeline and resource allocation for the BDPH Enterprise Platform, including the Web Application and Mobile Application ecosystem.

The project will be executed using a phased development approach to ensure scalability, modularity, and future enterprise expansion readiness.

## Resource Allocation Strategy

### Phase 1 — Web Application Development

Assigned resources: Developer 1, Developer 2

#### Scope Includes (Original)

- Core Platform Setup

- Authentication & User Management

- Dashboard Development

- GPS Tracking Integration

- Vehicle & Driver Management

- Trip & Operations Module

- Fuel, Tyre & Battery Management

- Billing & Accounts

- Inventory & Document Management

- Reports & Analytics

- Service History & Maintenance Modules

- Backend APIs

- Database Architecture

- Cloud Deployment Setup

Alerts & Notifications Page

Live Tracking: vehicle status counts, multi-vehicle map search, vendor/route filters, heading arrows, nearby vehicle identification

Trip & Operations: date/time on trips; driver reroute when route changes

Fuel: bulk Excel import; OCR API for driver fuel invoice capture

Inventory: part outward per vehicle; parts consumption analysis by vehicle

Vehicles: user-uploaded vehicle icons

Telematics: location-based idle detection; harsh acceleration events

#### Scope Includes (New — Web Components)

| Module | Web Deliverables |
| --- | --- |
| Share Vehicle Location | Generate time-limited tracking links from vehicle detail and fleet map; permission controls; audit log |
| Nearby Vehicle (Issue / Accident) | Incident map view; list nearest available vehicles when breakdown/accident is reported; dispatch actions |
| Breakdown Button | Web inbox for driver-reported breakdowns; auto-create issue/work order; live GPS pin on map |
| Fleet Mobile Application | API layer and admin configuration for mobile fleet operations (not the mobile UI itself) |
| Helper | Helper as contact classification; assign helper to vehicle/trip; helper profile in driver management |
| Two Drivers in One Vehicle | Primary + secondary driver (and optional helper) on vehicle assignment; trip crew roster; contact detail updates |
| Alerts Page | Dedicated alerts inbox with filters, severity, and acknowledgment |
| Live Tracking Enhancements | Status count chips; multi-vehicle search; vendor/route filters; heading arrows; nearby vehicles; idle/harsh events |
| Trip Date & Time | Start/end date-time on trip list and detail; sort and filter by window |
| Fuel Bulk Import | Excel template upload for batch fuel entries |
| Part Outward & Analytics | Link parts issued to vehicles; consumption ranking reports |
| Vehicle Icon Upload | Custom icons per vehicle on map and lists |
| Driver Reroute (Web) | Dispatch route change with audit trail and driver push notification |

#### Deliverables

- Fully functional responsive Web Application

- Backend APIs (including new incident, sharing, and multi-crew endpoints)

- Admin Dashboard

- Database Integration (dual-driver / helper schema)

- Initial Testing & QA

### Phase 2 — Mobile Application Development

Assigned resources: Developer 1, Developer 2

#### Scope Includes (Original)

- Android Mobile Application

- Driver Mobile Interface

- GPS Live Tracking

- Notifications & Alerts

- Trip Monitoring

- Basic Offline Synchronization

- Mobile Dashboard Integration

- API Connectivity with Web Platform

Driver app: fuel invoice photo upload with auto-populated fuel fields

Driver app: reroute notification and updated route when trip path changes

Driver/manager app: nearby vehicle list for any selected vehicle

Map: vehicle heading arrow and custom vehicle icons on mobile

#### Scope Includes (New — Mobile Components)

| Module | Mobile Deliverables |
| --- | --- |
| Share Vehicle Location | Driver can share live location link (SMS / WhatsApp / copy link) from assigned vehicle |
| Nearby Vehicle (Issue / Accident) | After breakdown, show nearest fleet vehicles to driver and dispatcher; tap-to-call / request backup |
| Breakdown Button | Prominent SOS / Breakdown button on driver home screen; one-tap GPS + vehicle + optional photo/notes; works offline with sync |
| Fleet Mobile Application | Android app for drivers (Phase 2A) and fleet managers / dispatchers (Phase 2B) — map, alerts, incident response, assignments |
| Helper | Helper can be linked to vehicle in mobile view; optional helper login with limited permissions (subject to client confirmation) |
| Two Drivers in One Vehicle | Both primary and secondary driver visible on trip; handoff / co-driver acknowledgment on mobile |
| Fuel Invoice OCR | Photo upload auto-fills fuel entry fields for driver review |
| Driver Reroute | Receive updated route when dispatch changes active trip path |
| Nearby Vehicles | View nearby fleet vehicles from any selected unit |
| Map UX | Vehicle heading arrow; custom uploaded vehicle icons |
| Alerts | Mobile alerts feed synced with web alerts page |

#### Deliverables

- Android Mobile Application (Driver + Fleet Manager views)

- Breakdown & emergency workflow (end-to-end)

- Share-location and nearby-vehicle features

- API Integration

- Mobile UI/UX

- Testing & Bug Fixing

- Deployment Support

## New Modules — Functional Specification

### 1. Share Vehicle Location

Allow authorized users to share a vehicle’s live GPS position with external parties (customer, broker, consignee) via a secure, time-limited link.

- Web: Share action on vehicle detail and fleet map; link expiry (e.g. 1h / 24h); revoke link

- Mobile: Share from driver app while on trip

- API: Public tracking token, rate limiting, audit trail

- Security: No login required for recipient; read-only map view

### 2. Nearby Vehicle (Issue / Accident)

When a breakdown or accident occurs, automatically surface nearest available vehicles to support backup, reassignment, or coordination.

- Trigger: Breakdown button or manual incident creation

- Logic: Geo-proximity search; filter by status (idle, available, en route)

- Web: Map + sorted list; dispatch / notify nearest unit

- Mobile: Driver sees nearby support options after reporting issue

### 3. Breakdown Button (Driver Application)

One-tap emergency / breakdown control in the driver mobile app.

- Captures: GPS, vehicle ID, driver ID, timestamp, optional notes/photo

- Creates: Incident + notification to fleet manager

- Triggers: Nearby vehicle search (Module 2)

- Supports: Offline queue with sync when connectivity returns

### 4. Fleet Mobile Application

Expanded mobile scope beyond driver-only interface.

| Sub-scope | Users | Key features |
| --- | --- | --- |
| Driver app | Drivers | Trips, fuel log, breakdown, share location, profile |
| Fleet manager app | Dispatchers, managers | Live map, incident alerts, nearby vehicles, approve assignments |

- Platform: Android (initial phase); iOS as future phase

- Integration: Full API connectivity with web platform

### 5. Helper

Support for a helper / crew member assigned to a vehicle or trip (e.g. attendant, loader, conductor).

- Helper registered as contact with Helper classification

- Can be assigned alongside drivers on vehicle assignment

- Permissions: TBD with client (view-only vs limited mobile access)

- Clarification required: Confirm helper role definition at kickoff

### 6. Two Drivers in One Vehicle

Support primary driver + secondary driver (co-driver) on the same vehicle and trip.

- Vehicle assignment: Operator (primary) + Co-driver (secondary)

- Trip dispatch: Both drivers linked to active trip

- Contact & assignment UI updated on web

- Mobile: Both drivers associated with vehicle; primary drives by default

- Clarification required: Whether both drivers use mobile app or primary only

## Additional Features — Functional Specification (Revision 3.0)

The following thirteen items were added in Revision 3.0 based on the latest client discussion (22 June 2026).

### 1. Fuel Invoice OCR (Driver App)

Module: Fuel | Platform: Mobile

When a driver uploads a fuel invoice/receipt photo in the driver app, the system automatically extracts and populates fuel entry fields (date, volume, amount, vendor, vehicle) with manual review before submit.

### 2. Part Outward & Parts Consumption Analysis

Module: Inventory | Platform: Web

Record which vehicle each part is issued to (part outward). Analytics to identify vehicles consuming the most parts by period, category, and cost for maintenance planning.

### 3. Bulk Fuel Entry (Excel Import)

Module: Fuel | Platform: Web

Import multiple fuel entries via Excel template upload with validation, error reporting, and duplicate detection.

### 4. Alerts Page

Module: Platform | Platform: Web + Mobile

Central alerts hub for fuel anomalies, document expiry, maintenance due, geofence breaches, idle time, harsh driving, breakdowns, and trip exceptions with read/unread and severity filters.

### 5. Vehicle Status Count (Live Tracking)

Module: Tracking | Platform: Web

Summary chips on Live Tracking showing live counts by status: Moving, Idle, Stopped, Offline, etc., synced with map filters.

### 6. Date & Time on Trip Page

Module: Trip & Operations | Platform: Web

Display scheduled/actual start and end date-time on trip list and trip detail; support sorting and filtering by trip window.

### 7. Location-Based Idle & Harsh Acceleration

Module: Tracking / Telematics | Platform: Web + Mobile

Detect and alert when a vehicle is idle at a specific location beyond threshold; flag harsh acceleration events with map pin, timestamp, and driver linkage.

### 8. Vehicle Icon Upload

Module: Vehicles | Platform: Web

Allow fleet admins to upload custom vehicle icons/images per vehicle or vehicle type for map and list views.

### 9. Vehicle Heading Arrow

Module: Tracking | Platform: Web + Mobile

Show directional heading arrow on map markers reflecting real-time vehicle bearing from GPS/telematics.

### 10. Multi-Vehicle Search (Live Tracking)

Module: Tracking | Platform: Web

Search bar supports selecting and tracking multiple vehicles simultaneously on the live map with combined list panel.

### 11. Nearby Vehicle Identification (All Vehicles)

Module: Tracking | Platform: Web + Mobile

For any selected vehicle, identify and list nearby fleet vehicles with distance, status, and quick contact/dispatch actions—not limited to breakdown scenarios.

### 12. Vendor & Route Filter (Live Tracking)

Module: Tracking | Platform: Web

Filter live map and vehicle list by vendor and route corridor; show only vehicles assigned to a particular vendor operating on a particular route.

### 13. Driver Reroute on Route Change

Module: Trip & Operations | Platform: Mobile + Web

When an active trip route is changed by dispatch, push updated route to driver app with turn-by-turn refresh, acknowledgment, and audit trail on web.

End of document